## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
User Login Screen | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | 1 | https://github.com/L1N6/Project-OnlineShop.git | Open | HieuTD | 2023-03-16 | 2022-04-18 16:45 | iter1 | Done | User Login
Write SRS for User Login screen | Write detailed functional specification for the User Login screen | 2 | https://github.com/L1N6/Project-OnlineShop.git | Closed | HieuTD | 2023-03-16 | 2022-04-18 16:45 | iter1 | Done | User Login
Write SDS for User Login screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the User Login screen | 3 | https://github.com/L1N6/Project-OnlineShop.git | Closed | HieuTD | 2023-03-16 | 2022-04-18 16:44 | iter1 | Done | User Login
Write Code for User Login screen | Code & Unit test for the User Login screen | 4 | https://github.com/L1N6/Project-OnlineShop.git | Open | HieuTD | 2023-03-16 | 2022-04-18 16:45 | iter1 | Done | User Login
Integrate User Login screen with others | Integrate the User Login screen with other screens | 5 | https://github.com/L1N6/Project-OnlineShop.git | Open | HieuTD | 2023-03-16 | 2022-04-18 16:45 | iter1 | Done | User Login
Home Screen | This is the landing page of the online shop. It typically includes an overview of the shop's products or services, as well as links to various categories of products. | 6 | https://github.com/L1N6/Project-OnlineShop.git | Closed | ThanhDQ | 2023-03-16 | 2022-04-18 16:45 | iter1 | Done | Home
Write SDS for User Home Screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the User Home Screen | 7 | https://github.com/L1N6/Project-OnlineShop.git | Closed | ThanhDQ | 2023-03-16 | 2022-04-18 16:44 | iter1 | Done | Home
Write SRS for User Home Screen | Write detailed functional specification for the User Login screen | 8 | https://github.com/L1N6/Project-OnlineShop.git | Closed | ThanhDQ | 2023-03-16 | 2022-04-18 16:45 | iter1 | Done | Home
Write Code for User Home Screen | Code & Unit test for the User Home Screen | 9 | https://github.com/L1N6/Project-OnlineShop.git | Open | ThanhDQ | 2023-03-16 | 2022-04-18 16:45 | iter1 | Done | Home
Contacting Screen | This function provides customers with a way to get in touch with the shop owner or customer support team. It may include a contact form, email address, or phone number. | 10 | https://github.com/L1N6/Project-OnlineShop.git |  | TungNT | 2023-03-16 |  | iter1 | Done | Contacting
Write SDS for User Contacting Screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the User Contacting Screen | 11 | https://github.com/L1N6/Project-OnlineShop.git |  | TungNT | 2023-03-16 |  | iter1 | Done | Contacting
Write SRS for User Contacting Screen | Write detailed functional specification for the User Contacting Screen | 12 | https://github.com/L1N6/Project-OnlineShop.git |  | TungNT | 2023-03-16 |  | iter1 | Done | Contacting
Write Code for User Contacting Screen | Code & Unit test for the User Contacting Screen | 13 | https://github.com/L1N6/Project-OnlineShop.git |  | TungNT | 2023-03-16 |  | iter1 | Done | Contacting
Product Detail Screen | This screen provides detailed information about a specific product, including images, descriptions, and specifications. | 14 | https://github.com/L1N6/Project-OnlineShop.git |  | TungTD | 2023-03-16 |  | iter1 | Done | Product Detail
Write SDS for User Detail Screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the User Detail Screen | 15 | https://github.com/L1N6/Project-OnlineShop.git |  | TungTD | 2023-03-16 |  | iter1 | Done | Product Detail
Write SRS for User Detail Screen | Write detailed functional specification for the User Detail Screen | 16 | https://github.com/L1N6/Project-OnlineShop.git |  | TungTD | 2023-03-16 |  | iter1 | Done | Product Detail
Write Code for User Detail Screen | Code & Unit test for the User Detail Screen | 17 | https://github.com/L1N6/Project-OnlineShop.git |  | TungTD | 2023-03-16 |  | iter1 | Done | Product Detail
Shop Screen | This is where customers can browse all of the products available for purchase on the online shop. It may include various filters and sorting options to help customers find the products they are looking for. | 18 | https://github.com/L1N6/Project-OnlineShop.git |  | LinhTQ | 2023-03-16 |  | iter1 | Done | Shop
Write SDS for User Shop Screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the User Shop Screen | 19 | https://github.com/L1N6/Project-OnlineShop.git |  | LinhTQ | 2023-03-16 |  | iter1 | Done | Shop
Write SRS for User Shop Screen | Write detailed functional specification for the User Shop Screen | 20 | https://github.com/L1N6/Project-OnlineShop.git |  | LinhTQ | 2023-03-16 |  | iter1 | Done | Shop
Write Code for User Shop Screen | Code & Unit test for the User Shop Screen | 21 | https://github.com/L1N6/Project-OnlineShop.git |  | LinhTQ | 2023-03-16 |  | iter1 | Done | Shop
Shopping Cart Screen | This is where customers can view the items they have added to their cart and proceed to checkout. | 22 | https://github.com/L1N6/Project-OnlineShop.git |  | LinhTQ | 2023-03-16 |  | iter1 | Done | Shopping Cart
Write SDS for User Shopping Cart Screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the User Shopping Cart Screen | 23 | https://github.com/L1N6/Project-OnlineShop.git |  | LinhTQ | 2023-03-16 |  | iter1 | Done | Shopping Cart
Write SRS for User Shopping Cart Screen | Write detailed functional specification for the User Shopping Cart Screen | 24 | https://github.com/L1N6/Project-OnlineShop.git |  | LinhTQ | 2023-03-16 |  | iter1 | Done | Shopping Cart
Write Code for User Shopping Cart Screen | Code & Unit test for the User Shopping Cart Screen | 25 | https://github.com/L1N6/Project-OnlineShop.git |  | LinhTQ | 2023-03-16 |  | iter1 | Done | Shopping Cart
Checkout Screen | This function enables customers to enter their shipping and payment information and complete their purchase. | 26 | https://github.com/L1N6/Project-OnlineShop.git |  | LinhTQ | 2023-03-16 |  | iter1 | Done | Checkout
Write SDS for User Checkout Screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the User Checkout Screen | 27 | https://github.com/L1N6/Project-OnlineShop.git |  | LinhTQ | 2023-03-16 |  | iter1 | Done | Checkout
Write SRS for User Checkout Screen | Write detailed functional specification for the User Checkout Screen | 28 | https://github.com/L1N6/Project-OnlineShop.git |  | LinhTQ | 2023-03-16 |  | iter1 | Done | Checkout
Write Code for User Checkout Screen | Code & Unit test for the User Checkout Screen | 29 | https://github.com/L1N6/Project-OnlineShop.git |  | LinhTQ | 2023-03-16 |  | iter1 | Done | Checkout