## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | User login | Common | User, Admin, Employee | This is a screen which allows the user to enter (email or username) & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it | HieuTD | Done | Done | None | None
2 | Hom | Public | User | Show homepage including: popular course, topic sections, expert section, feedback list, header, footer | ThanhDQ | Done | Done | None | None
3 | Contacting | Common | User | The customer and user can contact with shop here. | TungNT | Done | Done | None | None
4 | Shopping cart | Customer | User | The customer can order or add product in cart | LinhTQ | Done | Done | None | None
5 | Product detail | Common | User | User can see the detail of product | TungTD | Done | Done | None | None
6 | Checkout | Common | User | User payment | LinhTQ | Done | Done | None | None
7 | Shop | Common | User | This screen will show all the products | LinhTQ | Done | Done | None | None
6 | Account Profile | Common | Customer | Describes information based on the account the user is logged in with. | A hiếu | Done | Done | None | None
7 | Manage Admin | Admin | Admin | When you log in with an admin account, you can manage lower roles. For example: Product CRUD, Employee Management, … |  | To Do
8 | Manage Employee | Employee | Admin | When logged in with the employee account, lower roles can be managed. For example: order management, … | Thành | To Do
9 | Account Profile Update | Common | Customer, Employee | Update infor of account. | HieuTD | To Do
10 | Order History | Common | Admin | Show ordered of customers. | ThanhDQ | To Do
11 | Manage Product | Admin | Admin | CRUD product by Admin's Account. | ThanhDQ | To Do
12 | Admin DashBoard | Admin | Admin | Show the statistic of all orders | ThanhDQ | To Do
13 | List Product | Admin | Admin | Show All Product. | ThanhDQ | To Do
14 | Update Product | Admin | Admin | Update product | ThanhDQ | To Do
15 | Manage Account | Admin | Admin | Show all account in the system. Admin can CRUD account | ThanhDQ | To Do
16 | Manage Employee | Admin | Admin | CRU employee by admin | ThanhDQ | To Do
17 | Manage Orders | Admin | Admin, Employee | UR orders of customers | ThanhDQ | To Do
18 | View Change Product | Admin | Admin | Show history of product changed | ThanhDQ | To Do
19 | Manage Comment | Admin | Admin, Employee | UR comment of customers | ThanhDQ | To Do
20 | Create comment | Customer, Employee, Admin | Customer, Employee, Admin | This function allows commenting when an actor has logged into the system. | ThanhDQ | To Do
21 | View comment | Customer, Guest, Employee, Admin | Customer, Guest, Employee, Admin | This function allows actors to view comment of everybody | ThanhDQ | To Do
22 | Update comment | Customer, Employee, Admin | Customer, Employee, Admin | This function allows users to edit their comment when they have logged into the system and comment before | ThanhDQ | To Do
23 | Delete comment | Customer, Employee, Admin | Customer, Employee, Admin | This function allows actors to delete their comment when they have logged into the system and comment before | ThanhDQ | To Do
24 | View Order Change | Admin,Employee | Admin,Employee | This function allows actors to view history of order’s status | ThanhDQ | To Do

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | User login | Common | This is a screen which allows the user to enter (email or username) & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it | HieuTD | Done | Done | II.5
2 | Home | Public | Show homepage including: popular course, topic sections, expert section, feedback list, header, footer | ThanhDQ | Done | Done | II.1
3 | Contacting | Common | The customer and user can contact with shop here. | TungNT | Done | Done | II.4
4 | Shopping cart | Customer | The customer can order or add product in cart | LinhTQ | Done | Done | II.6
5 | Product detail | Common | User can see the detail of product | TungTD | Done | Done | II.2
6 | Checkout | Common | User payment | LinhTQ | Done | Done | II.7
7 | Shop | Common | This screen will show all the products | LinhTQ | Done | Done | II.3
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Account Profile | Common | Describes information based on the account the user is logged in with. | HieuTD | Done | Done
2 | Manage Admin | Admin | When you log in with an admin account, you can manage lower roles. For example: Product CRUD, Employee Management, … | ThanhTQ | To Do
3 | Manage Employee | Employee | When logged in with the employee account, lower roles can be managed. For example: order management, … | ThanhTQ | To Do
4 | Account Profile Update | Common | Update infor of account. | HieuTD | To Do
5 | Order History | Common | Show ordered of customers. | ThanhTQ | To Do
6 | Manage Product | Admin | CRUD product by Admin's Account. | ThanhTQ | To Do
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Admin DashBoard | Admin | Show the statistic of all orders | LinhTQ | To Do
2 | List Product | Admin | Show All Product. | ThanhTQ | To Do
3 | Update Product | Admin | Update product | ThanhTQ | To Do
4 | Manage Account | Admin | Show all account in the system. (Admin can CRUD account) | ThanhTQ | To Do
5 | Manage Employee | Admin | CRU employee by admin | ThanhTQ | To Do
6 | Manage Orders | Admin | UR orders of customers | ThanhTQ | To Do
7 | View Change Product | Admin | Show history of product changed | ThanhTQ | To Do
8 | Manage Comment | Admin | UR comment of customers | ThanhTQ | To Do
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Create comment | Customer, Employee, Admin | This function allows commenting when an actor has logged into the system. | ThanhDQ | To Do | To Do | To Do
2 | View comment | Customer, Guest, Employee, Admin | This function allows actors to view comment of everybody | ThanhDQ | To Do | To Do | To Do
3 | Update comment | Customer, Employee, Admin | This function allows users to edit their comment when they have logged into the system and comment before | ThanhDQ | To Do | To Do | To Do
4 | Delete comment | Customer, Employee, Admin | This function allows actors to delete their comment when they have logged into the system and comment before | ThanhDQ | To Do | To Do | To Do
5 | View Order Change | Admin,Employee | This function allows actors to view history of order’s status | ThanhDQ | To Do | To Do | To Do
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document