## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Screen/Function Name1 | Feature Name1 | Admin, Manager | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Updated | iter1 | iter2
2 | Screen/Function Name2 | Feature Name2 | Admin | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | Done | iter2 | none
3 | Screen/Function Name3 | Feature Name2 | Admin | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | Doing | iter3 | none
4 | User Login | Common | User | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Tử Vinh | To Do | iter4 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | User login | Common | This is a screen which allows the user to enter (email or username) & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it | A Hiếu | To Do
2 | Hom | Public | Show homepage including: popular course, topic sections, expert section, feedback list, header, footer | Thành | To Do
3 | Contacting | Common | The customer and user can contact with shop here. | T Tùng | To Do
4 | Shopping cart | Customer | The customer can order or add product in cart | Linh | To Do
5 | Product detail | Common | User can see the detail of product | Dương Tùng | To Do
6 | Checkout | Common | User payment | Linh | To Do
7 | Shop | Common | This screen will show all the products
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Profile | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Admin | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
3 | Admin | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
4 | Admin | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
5 | Admin | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document